## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Color
PROJECT: Improving Vehicular & Pedestrian Traffic Management using Cloud & Edge Computing and HPC
Capstone | SDLC Model: Iterative |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Tathagata Guha Ray
Project start date: | 2024-08-03 |  |  |  | September | [20 empty] | October | [27 empty] | November
Scrolling increment: | 44 | time axis 2024-09-16 to 2024-11-10
Milestone description | Category | Progress | Start | Days | time axis 2024-09-16 to 2024-11-10
Requirements Gathering & Analysis
Requirements Feasibility Analysis | Goal | 100% | 2024-08-05 | 2
Outline Objectives and Aim | Milestone | 100% | 2024-08-06 | 2
Prepare SRS Document | Med Risk | 100% | 2024-08-06 | 11
Gather Datasets | Goal | 30% | 2024-08-07 | 3
-
Planning & Design
Prepare High-Level Design | Low Risk | 100% | 2024-08-17 | 2
Create Class Diagram, State Machine Diagram, Sequence Diag. | Med Risk | 66% | 2024-08-19 | 4
-
-
Programming/Building
Program to Detect and Count vehicles & pedestrians | On Track | 100% | 2024-08-10 | 6
Plot above task over time-distribution curve | Milestone | 100% | 2024-08-16 | 2
Train custom model on dataset | Low Risk | 0% | 2024-08-18 | 2
Performance Analysis on Model | Low Risk | 70% | 2024-08-19 | 5
- |  |  | 1900-01-08 | 0
Programming/Building - Iter 2
Learn CloudSimPlus | Low Risk | 70% | 2024-09-22 | 14
Create basic class in CloudSimPlus | Low Risk | 60% | 2024-09-29 | 14
Create Zones | On Track | 100% | 2024-10-12 | 5
Assign Counter for Zones | On Track | 100% | 2024-10-16 | 3
Performance Analysis | Med Risk | 100% | 2024-10-19 | 4
Planning & Design
Update SRS Doc | Low Risk | 100% | 2024-10-24 | 3
Validate new Requirements | Med Risk | 100% | 2024-10-26 | 5
Programming/Building - Iter 3
Improve Performance for Inference and Per Frame times | Goal | 100% | 2024-11-01 | 7 | 2024-11-01: 2; 2024-11-02: 2; 2024-11-03: 2; 2024-11-04: 2; 2024-11-05: 2; 2024-11-06: 2; 2024-11-07: 2
Comparison between zones | High Risk | 100% | 2024-11-06 | 3
Add GUI instead of console | High Risk | 100% | 2024-11-09 | 7